## Project Management
Task | Starting Date | Finishing Date | No. of Days | % of Total Project Time | Labor Needed | No. of Working Hours/Day | $Rate/Hour | Total Labor Cost | % of Project Labor Cost | Equipment Needed | $Rate/Day/ Equipment | Total Equipment cost | Dsicount Rate for Cash Payment | Total Task Cost Before Discount | Total Task Cost After Discount
Surveying | 2018-01-01 | 2020-01-07 | 736 | 8.899% | 3 | 5 | 50 | 750 | 2.918% | 2 | 10000 | 14720000 | 10% | 14720750 | 13248675
Digging | 2018-01-08 | 2020-01-20 | 742 | 8.971% | 6 | 10 | 15.5 | 930 | 3.618% | 3 | 6000 | 13356000 | 6.5% | 13356930 | 12488729.55
Foundation | 2018-01-21 | 2020-02-20 | 760 | 9.189% | 10 | 12 | 20 | 2400 | 9.338% | 0 | 0 | 0 | 3.8% | 2400 | 2308.8
Frameworks | 2018-02-22 | 2020-02-25 | 733 | 8.862% | 20 | 12 | 15.75 | 3780 | 14.71% | 0 | 0 | 0 | 8.7% | 3780 | 3451.14
Construction | 2018-02-26 | 2020-04-05 | 769 | 9.298% | 20 | 12 | 20 | 4800 | 18.68% | 5 | 3500 | 13457500 | 2.4% | 13462300 | 13139204.8
Electricity | 2018-04-06 | 2020-04-23 | 748 | 9.044% | 5 | 8 | 30 | 1200 | 4.669% | 100 | 10.5 | 785400 | 7.5% | 786600 | 727605
Plumbing | 2018-04-24 | 2020-05-17 | 754 | 9.116% | 8 | 10 | 25 | 2000 | 7.781% | 150 | 36.8 | 4162080 | 4.9% | 4164080 | 3960040.08
Air Conditioning | 2018-05-18 | 2020-07-02 | 776 | 9.382% | 8 | 10 | 40 | 3200 | 12.45% | 20 | 119.5 | 1854640 | 1.5% | 1857840 | 1829972.4
Floors | 2018-07-03 | 2020-07-19 | 747 | 9.032% | 6 | 15 | 27.5 | 2475 | 9.63% | 1000 | 5.75 | 4295250 | 0% | 4297725 | 4297725
Painting | 2018-07-20 | 2020-07-28 | 739 | 8.935% | 4 | 12 | 16.5 | 792 | 3.081% | 200 | 16.25 | 2401750 | 3.5% | 2402542 | 2318453.03
Decorations | 2018-07-29 | 2020-09-03 | 767 | 9.273% | 9 | 10 | 37.5 | 3375 | 13.13% | 50 | 48.5 | 1859975 | 15% | 1863350 | 1583847.5
Total |  |  | 8271 |  |  |  |  | 25702 |  |  |  | 56892595 |  | 56918297 | 53600012.3

## Functions
Theta | X in (Radians) | F1 | F2 | F3 | F4 | F5 | F6
10 | 0.17453 | -1.4901 | 0.83099 | -20.4654 | -26.7311 | -0.3539 | 0.13992
20 | 0.34907 | -1.0051 | 0.80024 | 112.6725 | -0.88453 | 0.11394 | -0.99361
30 | 0.5236 | -0.36162 | 0.77526 | 255.2011 | 30.3867 | 0.57251 | -0.95292
40 | 0.69813 | 0.41022 | 0.75433 | 424.8665 | 1451.422 | 0.92198 | 0.30649
50 | 0.87266 | 1.2929 | 0.73639 | 629.6958 | 21502.4488 | 1.39 | -0.95529
60 | 1.0472 | 2.2747 | 0.72074 | 875.5513 | 226344.9156 | 1.8856 | 0.94904
70 | 1.2217 | 3.3469 | 0.7069 | 1167.5982 | 2074865.2716 | 1.2615 | -0.99801
80 | 1.3963 | 4.5028 | 0.69451 | 1510.7411 | 17864437.1578 | 1.0464 | 0.9079
90 | 1.5708 | 5.7369 | 0.68332 | 1909.7888 | 149291702.5726 | 0.91757 | 0.39532
100 | 1.7453 | 7.0447 | 0.67313 | 2369.5241 | 1229633964.1423 | 0.82603 | 0.17596
110 | 1.9199 | 8.4225 | 0.66379 | 2894.7371 | 10055691776.6547 | 0.755 | 0.91298
120 | 2.0944 | 9.867 | 0.65518 | 3490.2414 | 81943003118.2456 | 0.69684 | 0.32854
130 | 2.2689 | 11.3753 | 0.6472 | 4160.883 | 666575782955.1544 | 0.64746 | -0.90328
140 | 2.4435 | 12.9449 | 0.63976 | 4911.5438 | 5.4176e+12 | 0.60444 | -0.91765
150 | 2.618 | 14.5737 | 0.63282 | 5747.1439 | 4.4013e+13 | 0.56624 | 0.96911
160 | 2.7925 | 16.2594 | 0.6263 | 6672.6419 | 357483489559615 | 0.53183 | -0.33344
170 | 2.9671 | 18.0005 | 0.62016 | 7693.0351 | 2.9033e+15 | 0.50047 | -0.15782
180 | 3.1416 | 19.7951 | 0.61437 | 8813.3587 | 23577270595330632 | 0.47163 | -0.15779
190 | 3.3161 | 21.6418 | 0.60889 | 10038.6852 | 1.9146e+17 | 0.44489 | 0.2116
200 | 3.4907 | 23.5391 | 0.60369 | 11374.1235 | 1.5548e+18 | 0.41996 | -0.92688